## Terrier Trivia Tasks
Task Name | Due Date | Completed Date | Done | Assigned To | Status | Comments
HTML Code | 2019-12-01 | 2019-11-30 | TRUE | Esperanza | Complete
CSS Code | 2019-12-01 | 2019-11-30 | TRUE | Esperanza | Complete
Trivia Questions Coded | 2019-12-01 | 2019-12-01 | TRUE | Se'Lina Lasher | Complete
Create Question Function | 2019-11-29 | 2019-11-29 | TRUE | Se'Lina Lasher | Complete
Create Check Answer Function | 2019-11-29 | 2019-11-29 | TRUE | Se'Lina Lasher | Complete
Highscore and Total Score Coded | 2019-12-06 | 2019-12-05 | TRUE | Se'Lina Lasher | Complete
Button GUI Implemented | 2019-12-06 | 2019-12-04 | TRUE | Pooja | Complete
GUI Imagery Implemented | 2019-12-06 | 2019-12-05 | TRUE | Pooja | Complete
Video Recorded | 2019-12-11 | 2019-12-13 |  | Everyone | Not Started
Video Edited | 2019-12-11 | 2019-12-12 |  | Everyone | Not Started
Report | 2019-12-11 | 2019-12-11 |  | Everyone | In Progress
Make Mongo Database | 2019-12-06 | 2019-12-05 | TRUE | Alexandra | Complete
Implement Firebase in Android App | 2019-12-06 | 2019-12-10 | TRUE | Se'Lina L | In Progress
Implement Firebase in HTML Code | 2019-12-06 | 2019-12-10 | TRUE | Alexandra & Se'Lina | In Progress
Post Website with Github | 2019-12-06 | 2019-12-10 | TRUE | Alexandra | In Progress
Query Database | 2019-12-06 | 2019-12-10 | TRUE | Alexandra & Se'Lina | In Progress
Leadership Board Activity | 2019-12-07 | 2019-12-09 | TRUE | Vanessa | Complete
Meeting #1 | 2019-10-26 | 2019-10-26 | TRUE | Everyone | Complete
Meeting #2 | 2019-11-13 | 2019-11-13 | TRUE | Everyone | Complete
Meeting #3 | 2019-11-27 | 2019-11-27 | TRUE | Everyong | Complete
Meeting #4 | 2019-12-09 | 2019-12-09 | TRUE | Everyone | Complete